## Sheet1
Risk Description | Impact Description | Impact (1-5) | Probability (1-5) | Priority level(impact X probability) | Mitigation Notes | Owner
Customer data breach | Financial loss,reputational damage | 5 | 4 | 20 | Implement encryption,regular security testing | IT
Online payment system downtime | Loss sale and customer dissatisfaction | 4 | 3 | 12 | Add redundancy ,monitor systems 24/7 | IT
Non-Compliance with POPIA | Legal fines and customer trust issues | 4 | 4 | 16 | Conduct audits,train staff on POPIA | Compliance
Vendor dependency on cloud provider | Service disruption and data loss | 4 | 3 | 12 | Develop backup vendor relationships | Procurement
Insider threat from staff | Data leakage or sabotage | 4 | 3 | 12 | Use monitoring tools and strict HR policies | Security
In-store stock theft | Loss of inventory,financial impact | 3 | 4 | 12 | Install CCTV and conduct suprise checks | Store Manager
Inadequate access control | Unauthorized access to sensitive data | 5 | 4 | 20 | Enforce least privilege access,regular reviews | IT
[5 empty] | Impact: 1 | 2 | 3 | 4 | 5
|  |  |  | Prob: 5 (High) | 5 (G) | 10 (Y) | 15 (O) | 20 (R) | 25 (R)
|  |  |  | 4 | 4 (G) | 8 (Y) | 12 (Y) | 16 (O) | 20 (R)
|  |  |  | 3 | 3 (G) | 6 (G) | 9 (Y) | 12 (Y) | 15 (O)
|  |  |  | 2 | 2 (G) | 4 (G) | 6 (G) | 8 (Y) | 10 (Y)
|  |  |  | 1 (Low) | 1 (G) | 2 (G) | 3 (G) | 4 (G) | 5 (G)